## Sheet1
Sprint | Week | Task | Responsible Team Member
Sprint 1 | Week 1 | Project Planning & Requirement Analysis | Project Manager
Sprint 1 | Week 2 | Setup Django & React TS Environment | Backend Team
Sprint 1 | Week 3 | Design API Structure | Backend Team
Sprint 2 | Week 4 | Develop Authentication System (Backend) | Backend Team
Sprint 2 | Week 5 | Implement Authentication UI (Frontend) | Frontend Team
Sprint 2 | Week 6 | Create Database Models & Migrations | Backend Team
Sprint 3 | Week 7 | Develop Core API Features | Backend Team
Sprint 3 | Week 8 | Build Core Frontend Components | Frontend Team
Sprint 3 | Week 9 | Testing & Debugging | All Members
Sprint 4 | Week 10 | Enhance Features & Performance | All Members
Sprint 4 | Week 11 | Final Testing & Bug Fixes | All Members
Sprint 4 | Week 12 | Deployment & Documentation | All Members